## 📊 Dashboard
🎓 42 SCHOOL — PROJECT TRACKER
Deadline: 23 June 2026 • Start: 22 April 2026 • 62 Days
① CALL ME MAYBE · Python
Start Date | End Date | Duration | Language | Phase Count | Total Tasks
22 Apr 2026 | 09 May 2026 | 18 days | Python | 6 | 32
Progress: [ Track in the Daily Log sheet ]
② CODEXION · C
Start Date | End Date | Duration | Language | Phase Count | Total Tasks
10 May 2026 | 31 May 2026 | 22 days | C | 7 | 36
Progress: [ Track in the Daily Log sheet ]
③ FLY-IN · Python
Start Date | End Date | Duration | Language | Phase Count | Total Tasks
01 Jun 2026 | 22 Jun 2026 | 22 days | Python | 7 | 38
Progress: [ Track in the Daily Log sheet ]
STATUS LEGEND
⬜ To Do | 🟡 In Progress | ✅ Done | 🔴 Blocked | ⏭ Skipped

## ① Call Me Mayb
CALL ME MAYBE · Python · 18 days
Start: 22 Apr 2026 → End: 09 May 2026 ¦ Deadline: 23 Jun 2026
Phase | Task | Est. Hours | Status | % Done | Notes
▸ PLANNING & SETUP — 3 days
Planning & Setup | Read subject & understand constrained decoding concept | 0.5 | ⬜ To Do | 0%
Planning & Setup | Set up virtual env, install uv, numpy, pydantic | 0.5 | ⬜ To Do | 0%
Planning & Setup | Copy llm_sdk, explore vocabulary JSON structure | 0.5 | ⬜ To Do | 0%
Planning & Setup | Study Qwen3-0.6B tokenizer & encode/decode methods | 0.5 | ⬜ To Do | 0%
Planning & Setup | Design architecture: pipeline, decoder, output | 1 | ⬜ To Do | 0%
▸ PARSER & INPUT — 2 days
Parser & Input | Parse function_definitions.json with Pydantic models | 0.5 | ⬜ To Do | 0%
Parser & Input | Parse function_calling_tests.json input file | 0.5 | ⬜ To Do | 0%
Parser & Input | Handle malformed JSON & missing files gracefully | 0.5 | ⬜ To Do | 0%
Parser & Input | Write unit tests for parser edge cases | 0.5 | ⬜ To Do | 0%
▸ LLM PIPELINE — 4 days
LLM Pipeline | Implement tokenization → input_ids pipeline | 0.5 | ⬜ To Do | 0%
LLM Pipeline | Call get_logits_from_input_ids correctly | 0.5 | ⬜ To Do | 0%
LLM Pipeline | Build vocabulary map: token_id → string | 0.5 | ⬜ To Do | 0%
LLM Pipeline | Implement greedy / argmax token selection | 0.5 | ⬜ To Do | 0%
LLM Pipeline | Test basic generation loop end-to-end | 1 | ⬜ To Do | 0%
LLM Pipeline | Add type hints + mypy checks (must pass) | 0.5 | ⬜ To Do | 0%
LLM Pipeline | Add docstrings PEP 257 style | 0.5 | ⬜ To Do | 0%
▸ CONSTRAINED DECODING — 5 days
Constrained Decoding | Understand JSON grammar: which tokens are valid at each step | 1 | ⬜ To Do | 0%
Constrained Decoding | Build constraint mask for JSON structure (braces, quotes, colons) | 1 | ⬜ To Do | 0%
Constrained Decoding | Enforce schema: function name must match definitions | 1 | ⬜ To Do | 0%
Constrained Decoding | Enforce parameter types (number, string, boolean) | 1 | ⬜ To Do | 0%
Constrained Decoding | Set logits of invalid tokens to -inf before sampling | 0.5 | ⬜ To Do | 0%
Constrained Decoding | Test: 100% valid JSON output on all inputs | 0.5 | ⬜ To Do | 0%
▸ OUTPUT & QUALITY — 2 days
Output & Quality | Format output: prompt + name + parameters JSON array | 0.5 | ⬜ To Do | 0%
Output & Quality | Validate against schema rules (no extra keys, correct types) | 0.5 | ⬜ To Do | 0%
Output & Quality | Run flake8 & mypy --strict, fix all issues | 0.5 | ⬜ To Do | 0%
Output & Quality | Test accuracy: aim for 90%+ correct function selection | 0.5 | ⬜ To Do | 0%
Output & Quality | Benchmark speed: all prompts under 5 minutes | 0.5 | ⬜ To Do | 0%
▸ README & SUBMISSION — 2 days
README & Submission | Write Description, Instructions, Resources sections | 0.5 | ⬜ To Do | 0%
README & Submission | Document constrained decoding algorithm in detail | 0.5 | ⬜ To Do | 0%
README & Submission | Write design decisions & performance analysis | 0.5 | ⬜ To Do | 0%
README & Submission | Add Makefile: install, run, debug, clean, lint | 0.5 | ⬜ To Do | 0%
README & Submission | Final review, git push, double-check file names | 0.5 | ⬜ To Do | 0%
TOTAL ESTIMATED HOURS |  |  | ← Update Status & % Done as you work each task

## ② Codexion
CODEXION · C · 22 days
Start: 10 May 2026 → End: 31 May 2026 ¦ Deadline: 23 Jun 2026
Phase | Task | Est. Hours | Status | % Done | Notes
▸ PLANNING & SETUP — 3 days
Planning & Setup | Read full subject, understand all rules & args | 0.5 | ⬜ To Do | 0%
Planning & Setup | Sketch data structures: coder, dongle, monitor | 0.5 | ⬜ To Do | 0%
Planning & Setup | Plan thread model: N coder threads + 1 monitor thread | 0.5 | ⬜ To Do | 0%
Planning & Setup | Plan mutexes & condition variables layout | 0.5 | ⬜ To Do | 0%
Planning & Setup | Study FIFO vs EDF scheduling differences | 1 | ⬜ To Do | 0%
▸ ARGUMENT PARSING & STRUCTS — 3 days
Argument Parsing & Structs | Parse & validate all 8 mandatory arguments | 0.5 | ⬜ To Do | 0%
Argument Parsing & Structs | Reject negatives, non-integers, invalid scheduler string | 0.5 | ⬜ To Do | 0%
Argument Parsing & Structs | Define t_coder struct (id, state, timestamps, deadline) | 0.5 | ⬜ To Do | 0%
Argument Parsing & Structs | Define t_dongle struct (mutex, cond, cooldown, queue) | 0.5 | ⬜ To Do | 0%
Argument Parsing & Structs | Define t_simulation global state struct (no global vars!) | 0.5 | ⬜ To Do | 0%
Argument Parsing & Structs | Write error messages for invalid inputs | 0.5 | ⬜ To Do | 0%
▸ CORE SIMULATION — 5 days
Core Simulation | Implement pthread_create for each coder thread | 0.5 | ⬜ To Do | 0%
Core Simulation | Implement coder lifecycle: compile → debug → refactor → loop | 1 | ⬜ To Do | 0%
Core Simulation | Implement dongle pickup: left then right (deadlock-aware) | 1 | ⬜ To Do | 0%
Core Simulation | Implement dongle release + cooldown timer (dongle_cooldown ms) | 0.5 | ⬜ To Do | 0%
Core Simulation | Implement usleep-based timing for compile/debug/refactor durations | 0.5 | ⬜ To Do | 0%
Core Simulation | Add gettimeofday() timestamps to all logs | 0.5 | ⬜ To Do | 0%
Core Simulation | Serialize log output with mutex (no interleaved lines) | 0.5 | ⬜ To Do | 0%
▸ SCHEDULING (FIFO & EDF) — 5 days
Scheduling (FIFO & EDF) | Implement priority queue (min-heap) in C89 for scheduling | 1.5 | ⬜ To Do | 0%
Scheduling (FIFO & EDF) | FIFO: enqueue request timestamp, dequeue earliest arrival | 1 | ⬜ To Do | 0%
Scheduling (FIFO & EDF) | EDF: compute deadline = last_compile_start + time_to_burnout | 1 | ⬜ To Do | 0%
Scheduling (FIFO & EDF) | EDF: dequeue coder with earliest deadline first | 1 | ⬜ To Do | 0%
Scheduling (FIFO & EDF) | Test both schedulers with multiple coders | 0.5 | ⬜ To Do | 0%
▸ MONITOR & BURNOUT DETECTION — 3 days
Monitor & Burnout Detection | Implement separate monitor thread | 0.5 | ⬜ To Do | 0%
Monitor & Burnout Detection | Monitor checks each coder's time since last compile | 0.5 | ⬜ To Do | 0%
Monitor & Burnout Detection | Detect burnout within 10ms precision | 1 | ⬜ To Do | 0%
Monitor & Burnout Detection | Print burned out log ≤ 10ms after actual event | 0.5 | ⬜ To Do | 0%
Monitor & Burnout Detection | Stop simulation: burnout OR all coders hit compile count | 0.5 | ⬜ To Do | 0%
▸ MEMORY & NORM — 2 days
Memory & Norm | Free all heap memory, destroy all mutexes & conds | 0.5 | ⬜ To Do | 0%
Memory & Norm | Check for memory leaks (valgrind or similar) | 0.5 | ⬜ To Do | 0%
Memory & Norm | Ensure no global variables anywhere | 0.5 | ⬜ To Do | 0%
Memory & Norm | Compile with -Wall -Wextra -Werror -pthread, fix all warnings | 0.5 | ⬜ To Do | 0%
▸ TESTING & README — 1 days
Testing & README | Test edge case: 1 coder (only 1 dongle) | 0.5 | ⬜ To Do | 0%
Testing & README | Test: coder with very short time_to_burnout | 0.5 | ⬜ To Do | 0%
Testing & README | Write README: blocking cases, thread sync mechanisms | 0.5 | ⬜ To Do | 0%
Testing & README | Final git push, verify Makefile rules all work | 0.5 | ⬜ To Do | 0%
TOTAL ESTIMATED HOURS |  |  | ← Update Status & % Done as you work each task

## ③ Fly-in
FLY-IN · Python · 22 days
Start: 01 Jun 2026 → End: 22 Jun 2026 ¦ Deadline: 23 Jun 2026
Phase | Task | Est. Hours | Status | % Done | Notes
▸ PLANNING & SETUP — 2 days
Planning & Setup | Read subject, study all zone types & connection rules | 0.5 | ⬜ To Do | 0%
Planning & Setup | Study map file format thoroughly, note all metadata | 0.5 | ⬜ To Do | 0%
Planning & Setup | Set up Python 3.10+ env, plan OOP class hierarchy | 0.5 | ⬜ To Do | 0%
Planning & Setup | Choose pathfinding approach (BFS/Dijkstra/A* - no networkx!) | 0.5 | ⬜ To Do | 0%
▸ PARSER — 4 days
Parser | Parse nb_drones, start_hub, end_hub lines | 0.5 | ⬜ To Do | 0%
Parser | Parse hub: lines with all metadata (zone, color, max_drones) | 0.5 | ⬜ To Do | 0%
Parser | Parse connection: lines with optional max_link_capacity | 0.5 | ⬜ To Do | 0%
Parser | Handle comments (#), validate zone types | 0.5 | ⬜ To Do | 0%
Parser | Raise clear errors: line number + cause for any invalid input | 0.5 | ⬜ To Do | 0%
Parser | Detect duplicate connections (a-b and b-a) | 0.5 | ⬜ To Do | 0%
Parser | Validate no dashes in zone names | 0.5 | ⬜ To Do | 0%
Parser | Test parser on all provided maps + custom edge-case maps | 0.5 | ⬜ To Do | 0%
▸ GRAPH & DATA STRUCTURES — 3 days
Graph & Data Structures | Implement Zone class (name, x, y, type, color, max_drones) | 0.5 | ⬜ To Do | 0%
Graph & Data Structures | Implement Connection class (zone1, zone2, max_link_capacity) | 0.5 | ⬜ To Do | 0%
Graph & Data Structures | Implement Graph class (zones dict, adjacency, no networkx) | 1 | ⬜ To Do | 0%
Graph & Data Structures | Implement Drone class (id, position, path, state) | 0.5 | ⬜ To Do | 0%
Graph & Data Structures | Add type hints + mypy, docstrings PEP 257 | 0.5 | ⬜ To Do | 0%
▸ PATHFINDING ALGORITHM — 5 days
Pathfinding Algorithm | Implement Dijkstra/A* from scratch (no graph libs) | 1.5 | ⬜ To Do | 0%
Pathfinding Algorithm | Account for zone movement costs: normal=1, restricted=2, priority=1 | 0.5 | ⬜ To Do | 0%
Pathfinding Algorithm | Skip blocked zones entirely in pathfinding | 0.5 | ⬜ To Do | 0%
Pathfinding Algorithm | Find multiple disjoint paths for drone distribution | 1 | ⬜ To Do | 0%
Pathfinding Algorithm | Handle restricted zone 2-turn transit (drone MUST arrive next turn) | 1 | ⬜ To Do | 0%
Pathfinding Algorithm | Test pathfinding on easy maps | 0.5 | ⬜ To Do | 0%
▸ SIMULATION ENGINE — 5 days
Simulation Engine | Implement turn-by-turn simulation loop | 1 | ⬜ To Do | 0%
Simulation Engine | Enforce zone capacity (max_drones per zone per turn) | 0.5 | ⬜ To Do | 0%
Simulation Engine | Enforce connection capacity (max_link_capacity) | 0.5 | ⬜ To Do | 0%
Simulation Engine | Allow drones to wait in place when blocked | 0.5 | ⬜ To Do | 0%
Simulation Engine | Handle simultaneous drone movement correctly | 1 | ⬜ To Do | 0%
Simulation Engine | Implement output format: D<ID>-<zone> per turn | 0.5 | ⬜ To Do | 0%
Simulation Engine | Stop when all drones reach end zone | 0.5 | ⬜ To Do | 0%
▸ VISUALIZATION — 2 days
Visualization | Implement colored terminal output for drone positions | 1 | ⬜ To Do | 0%
Visualization | Show zone states and drone movements per turn | 0.5 | ⬜ To Do | 0%
Visualization | (Bonus) Graphical interface if time allows | 0.5 | ⬜ To Do | 0%
▸ BENCHMARKS & README — 1 days
Benchmarks & README | Test all easy maps: target ≤ 6-8 turns | 0.5 | ⬜ To Do | 0%
Benchmarks & README | Test medium maps: target ≤ 12-20 turns | 0.5 | ⬜ To Do | 0%
Benchmarks & README | Run flake8 + mypy, fix all issues | 0.5 | ⬜ To Do | 0%
Benchmarks & README | Write README: algorithm description, visual docs, resources | 0.5 | ⬜ To Do | 0%
Benchmarks & README | Final git push, verify all files at repo root | 0.5 | ⬜ To Do | 0%
TOTAL ESTIMATED HOURS |  |  | ← Update Status & % Done as you work each task

## 📅 Daily Log
📅 DAILY LOG — Fajr → Asr
62 Days ¦ 22 Apr 2026 → 23 Jun 2026 ¦ Fill each row at end of day
Day | Date | Project | Task Worked On | Status | Hours | % Done | Notes / Blockers
1 | 2026-04-22 | Call Me Maybe |  |  | 0
2 | 2026-04-23 | Call Me Maybe |  |  | 0
3 | 2026-04-24 | Call Me Maybe |  |  | 0
4 | 2026-04-25 | Weekend — Rest 🕌 | — | — | —
5 | 2026-04-26 | Weekend — Rest 🕌 | — | — | —
6 | 2026-04-27 | Call Me Maybe |  |  | 0
7 | 2026-04-28 | Call Me Maybe |  |  | 0
8 | 2026-04-29 | Call Me Maybe |  |  | 0
9 | 2026-04-30 | Call Me Maybe |  |  | 0
10 | 2026-05-01 | Call Me Maybe |  |  | 0
11 | 2026-05-02 | Weekend — Rest 🕌 | — | — | —
12 | 2026-05-03 | Weekend — Rest 🕌 | — | — | —
13 | 2026-05-04 | Call Me Maybe |  |  | 0
14 | 2026-05-05 | Call Me Maybe |  |  | 0
15 | 2026-05-06 | Call Me Maybe |  |  | 0
16 | 2026-05-07 | Call Me Maybe |  |  | 0
17 | 2026-05-08 | Call Me Maybe |  |  | 0
18 | 2026-05-09 | Weekend — Rest 🕌 | — | — | —
19 | 2026-05-10 | Weekend — Rest 🕌 | — | — | —
20 | 2026-05-11 | Codexion |  |  | 0
21 | 2026-05-12 | Codexion |  |  | 0
22 | 2026-05-13 | Codexion |  |  | 0
23 | 2026-05-14 | Codexion |  |  | 0
24 | 2026-05-15 | Codexion |  |  | 0
25 | 2026-05-16 | Weekend — Rest 🕌 | — | — | —
26 | 2026-05-17 | Weekend — Rest 🕌 | — | — | —
27 | 2026-05-18 | Codexion |  |  | 0
28 | 2026-05-19 | Codexion |  |  | 0
29 | 2026-05-20 | Codexion |  |  | 0
30 | 2026-05-21 | Codexion |  |  | 0
31 | 2026-05-22 | Codexion |  |  | 0
32 | 2026-05-23 | Weekend — Rest 🕌 | — | — | —
33 | 2026-05-24 | Weekend — Rest 🕌 | — | — | —
34 | 2026-05-25 | Codexion |  |  | 0
35 | 2026-05-26 | Codexion |  |  | 0
36 | 2026-05-27 | Codexion |  |  | 0
37 | 2026-05-28 | Codexion |  |  | 0
38 | 2026-05-29 | Codexion |  |  | 0
39 | 2026-05-30 | Weekend — Rest 🕌 | — | — | —
40 | 2026-05-31 | Weekend — Rest 🕌 | — | — | —
41 | 2026-06-01 | Fly-in |  |  | 0
42 | 2026-06-02 | Fly-in |  |  | 0
43 | 2026-06-03 | Fly-in |  |  | 0
44 | 2026-06-04 | Fly-in |  |  | 0
45 | 2026-06-05 | Fly-in |  |  | 0
46 | 2026-06-06 | Weekend — Rest 🕌 | — | — | —
47 | 2026-06-07 | Weekend — Rest 🕌 | — | — | —
48 | 2026-06-08 | Fly-in |  |  | 0
49 | 2026-06-09 | Fly-in |  |  | 0
50 | 2026-06-10 | Fly-in |  |  | 0
51 | 2026-06-11 | Fly-in |  |  | 0
52 | 2026-06-12 | Fly-in |  |  | 0
53 | 2026-06-13 | Weekend — Rest 🕌 | — | — | —
54 | 2026-06-14 | Weekend — Rest 🕌 | — | — | —
55 | 2026-06-15 | Fly-in |  |  | 0
56 | 2026-06-16 | Fly-in |  |  | 0
57 | 2026-06-17 | Fly-in |  |  | 0
58 | 2026-06-18 | Fly-in |  |  | 0
59 | 2026-06-19 | Fly-in |  |  | 0
60 | 2026-06-20 | Weekend — Rest 🕌 | — | — | —
61 | 2026-06-21 | Weekend — Rest 🕌 | — | — | —
62 | 2026-06-22 | Fly-in |  |  | 0
TOTAL HOURS LOGGED | [5 empty] | total hours